## Sheet1
Team Meetings | Hours | Task | Work | Hours | Task
2024-08-27 | 1.5 | Discussed project ideas, Initial documentation repository setup | 2024-09-07 | 1.5 | Began looking through Hackademia source code to understand how it works
2024-08-28 | 1 | Met with Dr. Gallagher to discuss his project idea | 2024-09-14 | 1.5 | Continued looking through Hackademia source code
2024-08-29 | 1 | Met with Giovanni to discuss his project idea of creating a C x86 emulator module for Hackademia | 2024-09-15 | 2 | Researched Assembly x86 intel and how to animate the registers
2024-09-10 | 2 | Discussed more details of the Hackademia C x86 emulator project with Giovanni & logistics, divided team roles | 2024-10-04 | 2 | Continued researching Assembly x86
2024-09-17 | 1.5 | Wrote user stories, created design diagrams | 2024-10-11 | 1 | Adjusted timeline to model future work projections
2024-09-24 | 1 | Created task list | 2024-10-28 | 0.5 | Created document outlining the animation process for the registers and stack
2024-10-01 | 1 | Created milestone list and discussed plan for implementation tasks | 2024-10-29 | 1 | Researched which animation tools to use
2024-10-07 | 0.5 | Wrote project constraints essay | 2024-11-01 | 0.5 | Looked at how to convert C to Assembly
2024-10-15 | 1.5 | Created Fall Design Presentation and recorded Fall Design Presentation | 2024-11-03 | 2 | Sketched possible redesign options
2024-10-29 | 1.5 | Discussed future tasks and reviewed team's progress | 2024-11-06 | 2 | Researched how to read the Assembly code and how to animate
2024-11-06 | 1 | Divided up tasks for Fall Design Report, reviewed team progress | 2024-11-10 | 2 | Revised my outline of how the animation process is going to work- added skeleton functions
2024-11-12 | 1 | Discussed final tasks for the semester | 2024-11-14 | 2 | Experimented with new functions locally (these did not work)
2024-11-19 | 1.5 | Reviewed progress on client-server communication, reviewed issues with Intel format code | 2024-11-17 | 1 | Sketched the redesign of the Assembly stack and registers
2024-11-26 | 1 | Meeting with Professor Giovani to review progress | 2024-11-23 | 2 | Created Project Abstract, Description, and updated my biography in Github repo, and created this spreadsheet
|  |  | 2024-12-01 | 2 | Senior Design Report
| Total Hours: | 40