## Sheet1
Task | Start Date | End Date | Duration
Investigate current client implementation | 2024-10-07 | 2024-10-21 | 2 weeks
Investigate current database implementation | 2023-10-15 | 2024-10-29 | 2 weeks
Investigate current server implementation | 2023-10-15 | 2024-10-21 | 1 week
Research server implementation language options | 2024-10-15 | 2024-10-28 | 2 weeks
Research assembly code formatting in memory | 2024-10-21 | 2024-10-28 | 1 week
Research GCC Compilation Process | 2024-10-21 | 2024-10-29 | 1 Week
Research Postgres database design options | 2024-10-29 | 2024-11-05 | 1 week
Develop basic server functionality | 2024-10-29 | 2024-11-18 | 3 weeks
Implement client process to send C code to server | 2025-01-13 | 2025-01-26 | 2 weeks
Design a process to parse and interpret assembly code | 2025-01-13 | 2025-02-10 | 4 weeks
Design database | 2025-01-20 | 2025-02-03 | 2 weeks
Develop server process to receive C code, compile, and send back assembly code | 2025-01-20 | 2025-02-10 | 3 weeks
Implement client process to receive assembly code from server | 2025-01-27 | 2025-02-09 | 2 weeks
Create database | 2024-02-03 | 2025-02-24 | 3 weeks
Experiment with new UI design | 2025-02-10 | 2025-03-03 | 3 weeks
Implement server process to receive C code from client | 2025-02-24 | 2025-03-03 | 1 Week
Research authentication methods | 2025-02-24 | 2025-03-10 | 3 weeks
Implement server process to send assembly code to client | 2025-03-03 | 2025-03-10 | 1 week
Test efficiency of code | 2025-03-03 | 2025-03-17 | 2 weeks
Design login and authentication system | 2025-03-03 | 2025-03-24 | 3 weeks
Test usability | 2025-03-24 | 2025-03-31 | 1 week
Milestone
Ability for the end user to enter C code and for the code to successfully compile. | 2025-01-13 | 2025-02-24 | 6 weeks
Ability for the end user to view assembly output from compiled C code with corresponding animation features. | 2025-01-13 | 2025-03-02 | 7 weeks
Ability for the program to provide a login feature that supports multiple users. | 2025-02-03 | 2025-03-24 | 7 weeks