## Fall 2024
Date: | Hours: | Task:
2024-08-27 | 1 | Initial team meeting, discussed project and advisor ideas
2024-08-28 | 1 | Met with Dr. Gallagher to discuss Neromorphic Constraint Satisfaction project, and discussed with team
2024-08-29 | 1 | Met with Jeremy Hill to discuss TA scheduling software (generally, scheduling with constraints) | Running total: | 45
2024-08-29 | 1 | Met with Dr. Abuaitah to discuss assembly code simulator/educational tool project, and discussed with team
2024-09-10 | 1 | Met with Dr. Abuaitah to discuss project logistics and expectations
2024-09-10 | 1 | Met with team to draft contract and decide roles
2024-09-12 | 1 | Individual Capstone Assessment
2024-09-14 | 0.5 | Individual Capstone Assessment
2024-09-15 | 0.5 | Access and clone Hackademia repository
2024-09-16 | 0.5 | Review design diagram examples
2024-09-17 | 2 | Write user stories and create design diagrams
2024-09-24 | 1 | Develop task lists
2024-10-01 | 1 | Develop Milestone List
2024-10-04 | 0.5 | Add tasks to Timeline and Effort Matrix
2024-10-05 | 1 | Clean-up Timeline and Effort Matrix
2024-10-07 | 1 | Write project constraints essay
2024-10-15 | 2 | Created and recorded Fall Design Presentation
2024-10-28 | 3 | Migrate existing Hackademia app to Vite, clean-up and document build process
2024-10-28 | 2 | Develop proof-of-concept server
2024-10-29 | 1.5 | Reviewed initial team research and assigned new tasks
2024-11-03 | 1.5 | Reviewed and provided feedback on other presentations, reviewed feedback on own presentation
2024-11-06 | 1 | Discussed assembly code animation and divided tasks for Fall Design Report
2024-11-06 | 0.5 | Scheduled meeting with project advisor and reached out for clarification on design report expectations
2024-11-11 | 0.5 | Update Hackademia README with Vite conversion documentation
2024-11-11 | 0.5 | Researched sending and receiving HTTP requests
2024-11-12 | 0.5 | Researched sending and receiving HTTP requests
2024-11-12 | 1 | Reviewed progress made on implementing GCC compilation process, database design, and server
2024-11-12 | 1 | Re-construct meeting minutes and audit time spent on project so far
2024-11-13 | 1 | Experiment with sending and receiving HTTP requests
2024-11-19 | 1.5 | Reviewed issues with GCC compilation and progress on client-server communication, discussed future tasks
2024-11-21 | 0.5 | Discussed progress and server technologies with Dr. Abuaitah
2024-11-21 | 1 | Researched NodeJS versus Flask performance and discussed trade-offs with Dr. Abuaitah
2024-11-26 | 1 | Meeting with Dr. Abuaitah to discuss plans for interpreting compiled machine code
2024-11-30 | 3 | Revised group documents for final report
2024-12-01 | 1 | Revised individual documents for final report
2024-12-03 | 1 | Semester wrap-up meeting, discuss plans for end of semester, schedule for next semester
2024-12-10 | 1.5 | Created Node server, ported Flask server functionality to Node
2024-12-12 | 0.5 | Merge pull request, general repository organization
2024-12-13 | 1.5 | Review callstack and architecture resources
2024-12-13 | 1.5 | Review assembly code resources

## Spring 2025
Date: | Hours: | Task:
2025-01-13 | 0.25 | Complete team registration form for CEAS Expo
2025-01-15 | 1 | Discuss methods of disassembling machine code with advisor
2025-01-15 | 1 | Set up Virtual Machine as runtime environment for Hackademia | Running total: | 77
2025-01-16 | 2 | Investigated new server implementation
2025-01-17 | 0.5 | Set up Virtual Machine as runtime environment for Hackademia
2025-01-17 | 0.75 | Experiment with compiling C code and inspecting output patterns
2025-01-18 | 0.5 | Investigated new server implementation
2025-01-19 | 0.25 | C code compilation process
2025-01-22 | 0.75 | Discuss frontend style library options with advisor
2025-01-23 | 2.5 | Team meeting to discuss progress and hold-ups, work on C code compilation process
2025-01-23 | 0.5 | Discuss methods of disassembling machine code with advisor
2025-01-24 | 0.75 | Met with Pratik to discuss new server implementation
2025-01-30 | 1.5 | Team meeting to discuss new server structure, class assignments, and plans for further development
2025-01-30 | 1.25 | Implement "compile" API route
2025-02-02 | 0.25 | Review test plan
2025-02-05 | 4.25 | Implement C code compilation process
2025-02-06 | 1.75 | Integrated C code compilation with client changes and discussed future development plans
2025-02-09 | 0.75 | User Documentation
2025-02-09 | 0.5 | Time Tracking
2025-02-12 | 2.5 | Update compilation function to handle multiple functions of C code
2025-02-13 | 1 | Meet to sync up with team and discuss upcoming work assignments and homework tasks
2025-02-13 | 2.75 | Refactor code for Dynamic Callstack Component
2025-02-14 | 0.5 | Work on Expo slide deck
2025-02-17 | 1 | Reviewed progress and plans to interpret assembly code with advisor
2025-02-18 | 2.25 | Added 32-bit compilation and better error handling
2025-02-19 | 1 | Fix issues with library includes and filtering for functions when compiling 32-bit code
2025-02-20 | 1.25 | Meeting to sync up with the rest of the team and discuss how to merge divergent branches of work
2025-02-20 | 0.5 | Troubleshot and fixed filtering of 32-bit functions
2025-02-24 | 0.5 | Add basic information to expo poster
2025-02-24 | 1 | Researched assembly instructions and discussed project progress with team
2025-02-24 | 0.75 | Discuss methods of emulating assembly instructions and displaying memory values with advisor
2025-02-26 | 0.25 | Researched assembly instructions
2025-02-27 | 1.5 | Team meeting to sync up on tasks and troubleshoot environments
2025-02-27 | 1 | Work on parsing assembly instructions to determine proper implementation
2025-03-02 | 0.5 | Reviewed expo poster design
2025-03-05 | 0.75 | Experiment with assembly instruction implementation
2025-03-06 | 1 | Team meeting to sync up on tasks and determine work to be completed before expo
2025-03-09 | 3.75 | Investigated available information for each assembly instruction from the Iced API
2025-03-10 | 1 | Met with advisor to discuss best ways of getting operands of each assembly instruction
2025-03-12 | 2.75 | Implement case structure to parse and emulate common assembly instructions
2025-03-13 | 1 | Meet to sync up with team on tasks and plan work to be done over spring break
2025-03-18 | 1.25 | Implemented structures to handle different data type numbers, and unsupported instructions
2025-03-18 | 0.5 | Implement POP and ADD instructions
2025-03-19 | 2.25 | Investigate Iced handling of memory addresses, and set up instruction pointer
2025-03-20 | 2.25 | Refine disassembly process to associate address and state with each instruction
2025-03-26 | 1.75 | Met to sync up with team on tasks that had been accomplished over spring break, and work to be done
2025-03-30 | 1.25 | Resolve merge conflict
2025-03-31 | 2.25 | Implement 32-bit register operations for 64-bit assembly code
2025-03-31 | 0.75 | Troubleshoot state updating after each instruction
2025-03-31 | 1.25 | Met with advisor to discuss project status and plans before expo
2025-04-01 | 0.5 | Resolve merge conflict
2025-04-03 | 3 | Unified work from various team members tasks, discussed final action items before the expo
2025-04-03 | 0.25 | Time Tracking
2025-04-06 | 2.5 | Divided final report work and continued work on associating addresses with each instruction
2025-04-07 | 3.25 | Discussed final report work and troubleshot final errors
2025-04-07 | 3 | Implemented proper stack visualization for values that are stored relative to the base pointer
2025-04-14 | 1.5 | Final self assessment and report updates