## Preston
Date: | Hours: | Task:
2024-08-27 | 1 | Initial team meeting, discussed project and advisor ideas
2024-08-28 | 1 | Met with Dr. Gallagher to discuss Neromorphic Constraint Satisfaction project, and discussed with team
2024-08-29 | 1 | Met with Jeremy Hill to discuss TA scheduling software (generally, scheduling with constraints) | Running total: | 39
2024-08-29 | 1 | Met with Dr. Abuaitah to discuss assembly code simulator/educational tool project, and discussed with team
2024-09-10 | 1 | Met with Dr. Abuaitah to discuss project logistics and expectations
2024-09-10 | 1 | Met with team to draft contract and decide roles
2024-09-12 | 1 | Individual Capstone Assessment
2024-09-14 | 0.5 | Individual Capstone Assessment
2024-09-15 | 0.5 | Access and clone Hackademia repository
2024-09-16 | 0.5 | Review design diagram examples
2024-09-17 | 2 | Write user stories and create design diagrams
2024-09-24 | 1 | Develop task lists
2024-10-01 | 1 | Develop Milestone List
2024-10-04 | 0.5 | Add tasks to Timeline and Effort Matrix
2024-10-05 | 1 | Clean-up Timeline and Effort Matrix
2024-10-07 | 1 | Write project constraints essay
2024-10-15 | 2 | Created and recorded Fall Design Presentation
2024-10-28 | 3 | Migrate existing Hackademia app to Vite, clean-up and document build process
2024-10-28 | 2 | Develop proof-of-concept server
2024-10-29 | 1.5 | Reviewed initial team research and assigned new tasks
2024-11-03 | 1.5 | Reviewed and provided feedback on other presentations, reviewed feedback on own presentation
2024-11-06 | 1 | Discussed assembly code animation and divided tasks for Fall Design Report
2024-11-06 | 0.5 | Scheduled meeting with project advisor and reached out for clarification on design report expectations
2024-11-11 | 0.5 | Update Hackademia README with Vite conversion documentation
2024-11-11 | 0.5 | Researched sending and receiving HTTP requests
2024-11-12 | 0.5 | Researched sending and receiving HTTP requests
2024-11-12 | 1 | Reviewed progress made on implementing GCC compilation process, database design, and server
2024-11-12 | 1 | Re-construct meeting minutes and audit time spent on project so far
2024-11-13 | 1 | Experiment with sending and receiving HTTP requests
2024-11-19 | 1.5 | Reviewed issues with GCC compilation and progress on client-server communication, discussed future tasks
2024-11-21 | 0.5 | Discussed progress and server technologies with Dr. Abuaitah
2024-11-21 | 1 | Researched NodeJS versus Flask performance and discussed trade-offs with Dr. Abuaitah
2024-11-26 | 1 | Meeting with Dr. Abuaitah to discuss plans for interpreting compiled machine code
2024-11-30 | 3 | Revised group documents for final report
2024-12-01 | 1 | Revised individual documents for final report