## Sheet1
Team Meetings | Hours | Task | Work/Assignment Time |  | Task
2024-08-27 | 1.5 hours | Discussed project ideas, Initial documentation repository setup | 2024-09-07 | 2 hours | Reviewed previously implemented code setting up server and database connection
2024-08-28 | 1 hour | Met with Dr. Gallagher to discuss his project idea | 2024-09-20 | 1 hour | Researched database design options that are free
2024-08-29 | 1 hour | Met with Giovanni to discuss his project idea of creating a C x86 emulator module for Hackademia | 2024-09-21 | 1 hour | Looked into working with Postgres, pgAdmin, pgModeler, and MySQL
2024-09-10 | 2 hours | Discussed more details of the Hackademia C x86 emulator project with Giovanni & logistics, divided team roles | 2024-10-05 | 1.5 hours | Continued researching previous options
2024-09-17 | 1.5 hours | Wrote user stories, created design diagrams | 2024-10-16 | 2 hours | Decided to use SQLite and figured out how to install and use it
2024-09-24 | 1 hour | Created task list | 2024-10-27 | 1 hour | Continued to learn how to use SQLite
2024-10-01 | 1 hour | Created milestone list and discussed plan for implementation tasks | 2024-11-01 | 2 hours | Worked on deciding what aspects of the database need to be created
2024-10-07 | 0.5 hours | Wrote project constraints essay | 2024-11-05 | 2 hours | Researching how we can save user data and their code for continued usage in the database
2024-10-15 | 1.5 hours | Created Fall Design Presentation and recorded Fall Design Presentation | 2024-11-10 | 1 hour | Created the Hackademia database in SQLite
2024-10-29 | 1.5 hours | Discussed future tasks and reviewed team's progress | 2024-11-11 | 1 hour | Create the tables and columns in SQLite and foreign key connections
2024-11-06 | 1 hour | Divided up tasks for Fall Design Report, reviewed team progress | 2024-11-17 | 1 hour | Edited and played around with what values might be helpful to have within the database
2024-11-12 | 1 hour | Discussed final tasks for the semester | 2024-11-20 | 1 hour | Started researching how to create a runnable script that makes the database that anyone can run
2024-11-19 | 1.5 hours | Reviewed progress on client-server communication, reviewed issues with Intel format code | 2024-11-25 | 2 hours | Continuing to research and try to implement a new script for database creation
2024-11-26 | 1.5 hours | Meeting with Professor Giovani to review progress | 2024-11-27 | 2 hours | Redesigning/rethinking what we need in the database/ importance of implementing it rightnow
|  |  | 2024-11-28 | 2 hours | Revising essays and continuing to make edits
|  |  | 2024-11-29 | 3 hours | Researching how assembly compiles/emulators
|  |  | 2024-11-30 | 0.5 hours | Researching how assembly compiles/emulators
| Meeting Total: |  | Work Total: | 26
17.5