## Sheet1
Team Meetings | Hours | Task | Work/Assignment Time |  | Task
2024-08-27 | 1.5 hours | Discussed project ideas, Initial documentation repository setup | 2024-09-07 | 2 hours | Reviewed previously implemented code setting up server and database connection
2024-08-28 | 1 hour | Met with Dr. Gallagher to discuss his project idea | 2024-09-20 | 1 hour | Researched database design options that are free
2024-08-29 | 1 hour | Met with Giovanni to discuss his project idea of creating a C x86 emulator module for Hackademia | 2024-09-21 | 1 hour | Looked into working with Postgres, pgAdmin, pgModeler, and MySQL
2024-09-10 | 2 hours | Discussed more details of the Hackademia C x86 emulator project with Giovanni & logistics, divided team roles | 2024-10-05 | 1.5 hours | Continued researching previous options
2024-09-17 | 1.5 hours | Wrote user stories, created design diagrams | 2024-10-16 | 2 hours | Decided to use SQLite and figured out how to install and use it
2024-09-24 | 1 hour | Created task list | 2024-10-27 | 1 hour | Continued to learn how to use SQLite
2024-10-01 | 1 hour | Created milestone list and discussed plan for implementation tasks | 2024-11-01 | 2 hours | Worked on deciding what aspects of the database need to be created
2024-10-07 | 0.5 hours | Wrote project constraints essay | 2024-11-05 | 2 hours | Researching how we can save user data and their code for continued usage in the database
2024-10-15 | 1.5 hours | Created Fall Design Presentation and recorded Fall Design Presentation | 2024-11-10 | 1 hour | Created the Hackademia database in SQLite
2024-10-29 | 1.5 hours | Discussed future tasks and reviewed team's progress | 2024-11-11 | 1 hour | Create the tables and columns in SQLite and foreign key connections
2024-11-06 | 1 hour | Divided up tasks for Fall Design Report, reviewed team progress | 2024-11-17 | 1 hour | Edited and played around with what values might be helpful to have within the database
2024-11-12 | 1 hour | Discussed final tasks for the semester | 2024-11-20 | 1 hour | Started researching how to create a runnable script that makes the database that anyone can run
2024-11-19 | 1.5 hours | Reviewed progress on client-server communication, reviewed issues with Intel format code | 2024-11-25 | 2 hours | Continuing to research and try to implement a new script for database creation
2024-11-26 | 1.5 hours | Meeting with Professor Giovani to review progress | 2024-11-27 | 2 hours | Redesigning/rethinking what we need in the database/ importance of implementing it rightnow
|  |  | 2024-11-28 | 2 hours | Revising essays and continuing to make edits
|  |  | 2024-11-29 | 3 hours | Researching how assembly compiles/emulators
|  |  | 2024-11-30 | 0.5 hours | Researching how assembly compiles/emulators
| Meeting Total: |  | Work Total: | 26 |  | Fall Semester Total | 43.5
17.5
| Spring 2025 |  |  | Spring 2025
Team Meetings | Hours | Task | Work/Assignment Time (Hours) |  |  | Task
2025-01-15 | 1 | Meeting with Giovanni | 2025-01-20 | 3 | Look through and understand the front end changes with Typescript conversion and seeing what needs to be overhauled
2025-01-16 | 1 | Team Meeting | 2025-01-21 | 3 | Worked on creating test cases for the first assignment
2025-01-23 | 1 | Team Meeting | 2025-01-22 | 2.5 | Continued to create test cases and continued working on assignment 1
2025-01-30 | 1 | Team Meeting | 2025-01-24 | 2 | Adding in more test cases, and creating test case matrix for assignment 1
2025-02-06 | 1 | Team Meeting | 2025-01-25 | 3 | Looked into how to use bootsrap components to reformat and simplify code implementation
2025-02-13 | 1 | Team Meeting | 2025-01-25 | 1 | Finished Assignment 1
2025-02-17 | 1 | Meeting with Giovanni | 2025-01-27 | 2 | Worked on formatting for UI for dynamic call stack page
2025-02-27 | 1 | Team Meeting | 2025-01-28 | 2 | Continued to work on UI design and code refactoring
2025-03-06 | 1 | Team Meeting | 2025-01-29 | 1.5 | UI redesign
2025-03-26 | 2 | Team Meeting | 2025-02-01 | 1.5 | UI Deisgn
2025-03-31 | 2 | Team Meeting & Meeting with Giovanni to go over progress | 2025-02-05 | 2 | changing the way the file structure is
2025-04-03 | 1 | Team Meeting | 2025-02-10 | 2 | pulling new changes down, implementing csss fiile
2025-04-06 | 3 | Team Working Session | 2025-02-11 | 1.5 | Still working on UI design changes
2025-04-07 | 2 | Final pre expo working session | 2025-02-15 | 3 | Assignment 3 Work
2025-04-14 | 1 | Presenting final progress to Giovanni | 2025-02-16 | 2.5 | UI Error work
|  |  | 2025-02-17 | 2 | UI Error work
|  |  | 2025-02-20 | 1 | Attempting to merge code and fix issues
|  |  | 2025-02-24 | 1 | Started Poster
|  |  | 2025-02-26 | 1 | Meeting with teammate to go over next steps
Total Meeting Hours |  | 20 | 2025-03-01 | 2 | Fixing UI
|  |  | 2025-03-02 | 2 | Wrapping up the poster
|  |  | 2025-03-06 | 2 | Making more UI tweaks
|  |  | 2025-03-08 | 2 | Redesigning poster to resize
|  |  | 2025-03-14 | 2 | More poster changes
|  |  | 2025-03-16 | 1.5 | changing the scroll aspects
|  |  | 2025-03-20 | 3 | Final poster submission
|  |  | 2025-04-01 | 2 | Creating the pop error box for unsupported operands and instructions
|  |  | 2025-04-02 | 2 | Finishing and testing the pop up error box
|  |  | 2025-04-08 | 2 | Working on the self assessment assignment
|  |  | 2025-04-09 | 3 | Working on updating design diagrams, the test case results, and my time sheet
|  |  |  | 61 |  | Spring Semester Total: 81 hours